## Login Tests
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Login Testing | HIGH | 1 | 1 | 2024-03-14 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing how the login system works |  | Dominik Subocz | Dominik Subocz | 2024-03-14 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
During this test, small tests will be carried out testing different scenarios for login system to see if it works as it should.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Login with correct credentials. | 2024-03-14 | User logs in successfully, gets redirected to their profile. | User logs in successfully, but doesn't get redirected | PASS | Add redirection to their profile page.
2 | Login with correct credentials. (Admin) | 2024-03-14 | User logs in successfully, with admin priveledges, gets redirected to dashboard. | User logs in successfully, with admin priveledges, but doesn't get redirected | PASS | Add redirection to their profile page.
3 | Try to log in without entering some fields | 2024-03-14 | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | PASS | Fix the styling.
4 | Click link to register | 2024-03-14 | User should be redirected to the registration page. | User was redirected to the registration page. | PASS | Center the text using css
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE
| Login Testing | HIGH | 1 | 2 | 2024-04-10
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE
| Testing how the login system works |  | Dominik Subocz | Dominik Subocz | 2024-04-10
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
During this test, small tests will be carried out testing different scenarios for login system to see if it works as it should.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Login with correct credentials. (Coach) | 2024-03-14 | User logs in successfully, with coach priveledges, gets redirected to their profile page. | User logs in successfully, with coach priveledges, gets redirected to their profile page. | PASS

## Register Tests
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Registration Testing | HIGH | 2 | 1 | 14/03/204 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing how the register system works |  | Dominik Subocz | Dominik Subocz | 14/03/204 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
During this test, small tests will be carried out testing different scenarios for registration system to see if it works as it should.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Register an account, enter new credentials | 14/03/204 | User will be redirected to another web page to prompt their details | User gets redirected to another web page to prompt their details | PASS
2 | Enter more details, including the credentials previously entered and proceed | 14/03/205 | User will be redirected to a success page, with a message saying "Registration successful" | User gets redirected to a success page, with a message saying "Registration successful" | PASS | Apply some css styling
3 | Click on return to home page link, or wait until redirected automatically | 14/03/206 | User should be automatically redirected to logout page. | User does not get redirected automatically, user was redirected to invalid page. | FAIL | It techincally is a pass, but given the fact that it didn’t redirect user automatically, and it redirected them to wrong page I decided to put it as "FAIL"
4 | Register an account, enter already existing player's credentials | 14/03/207 | User should be automatically redirected to their profile page, and assigned user id. | User does not get redirected to their profile, but when clicking on the profile link, user gets redirected to correct profile, meaning user id was assigned correctly | PASS | Add automatic redirection
5 | Register an account, enter already existing junior player's credentials | 14/03/208 | User should be automatically redirected to their profile page, and assigned user id. | User does not get redirected to their profile, but when clicking on the profile link, user gets redirected to correct profile, meaning user id was assigned correctly | PASS | Add automatic redirection
6 | Register an account, enter already existing junior member's credentials | 14/03/209 | User should be automatically redirected to their profile page, and assigned user id. | User does not get redirected to their profile, but when clicking on the profile link, user gets redirected to correct profile, meaning user id was assigned correctly | PASS | Add automatic redirection
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE
| Registration Testing | HIGH | 2 | 2 | 2024-04-10
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE
| Testing how the register system works |  | Dominik Subocz | Dominik Subocz | 2024-04-10
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
During this test, small tests will be carried out testing different scenarios for registration system to see if it works as it should.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
3 | Click on return to home page link, or wait until redirected automatically | 2024-04-10 | User should be automatically redirected to logout page. | User gets automatically redirected to logout page. | PASS | User now gets redirected

## Timetable Tests
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Timetable Testing | MEDIUM | 3 | 1 | 2024-03-14 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing how the timetable system works |  | Dominik Subocz | Dominik Subocz | 2024-03-14 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| During this test, small tests will be carried out testing different scenarios for timetable system to see if it works as expected. |  | Login.php - user must be logged in.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Try to schedule a game | 2024-03-14 | Game is scheduled and appears on timetable. | Game isn't being scheduled and does not appear on the timetable. | FAIL | Fix booking game php script
2 | Try to schedule a game before today's date | 2024-03-14 | User shouldn't be able to book a game for date before today's date. | Game isn't being scheduled and does not appear on the timetable. Nothing happens. | FAIL | Fix booking game php script
3 | Try to schedule a game for more than 1 hour | 2024-03-14 | Time should update in the modal, and user should be able to see it before booking. | Time is updated in the modal | PASS
5 | Try to remove game | 2024-03-15 | Game should disapear from timetable | Can't add a game so can't remove it either | FAIL | Fix add game option, add remove game option
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE
| Timetable Testing | MEDIUM | 3 | 2 | 2024-04-10
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE
| Testing how the timetable system works |  | Dominik Subocz | Dominik Subocz | 2024-04-10
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| During this test, small tests will be carried out testing different scenarios for timetable system to see if it works as expected. |  | Login.php - user must be logged in.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Try to schedule a game | 2024-04-10 | Game is scheduled and appears on timetable. | Game is scheduled and appears on timetable. | PASS
2 | Try to schedule a game before today's date | 2024-04-10 | Error message "Invalid date" displayed | Game is scheduled and appears on timetable. | FAIL | Fix this issue in future update
3 | Try to remove game | 2024-04-10 | Game should disapear from timetable | Game disapears from timetable | PASS

## List & Profile Testing
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Player list & profile testing | MEDIUM | 4 | 1 | 2024-03-19 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing player list and profile |  | Dominik Subocz | Dominik Subocz | 2024-03-19 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| During this test, small tests will be carried out to see if the player list and player profile work as expected. This includes players, juniors and members. |  | Login.php - user must be logged in.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | A member tries to access any of the list pages | 2024-03-19 | User should be redirected to logout page | User can access this page and doesn't get redirected | FAIL | Add role verification for this page
2 | Admin/coach click on one of the profiles in the list. | 2024-03-19 | Admin/coach should get redirected to the php page of that player - displaying information for that player | Admin/coach get redirected to the php page of that player - displaying information for that player | PASS
3 | A member gets redirected to their profile page. | 2024-03-19 | Member should see information about them - they shouldn't be able to see or click remove or update buttons | Member sees information about them, they also see remove and update buttons | FAIL | Add role verification for this page
4 | Admin clicks on one of the player/junior/member profile | 2024-03-19 | Admin should see information about that member as well as a remove and update button | Admin sees information about that member as well as a remove and update button | PASS
5 | A coach clicks on one of the player/junior/member profile | 2024-03-19 | Coach should see information about that player - they should also see a button to update skill profile | Coach see information about that player - they see remove and update button | PASS | Add role verification for this page, add update skill profile button
6 | Admin clicks on the remove button | 2024-03-19 | A modal should appear asking admin if they're sure they want to delete the player | A modal appears asking admin if they're sure they want to delete the player | PASS
7 | Admin clicks the confirm delete button in modal | 2024-03-19 | Player should get deleted from database and get removed from the list | Player gets deleted from database and gets removed from the list. (Requires refresh) | PASS
8 | Admin clicks the cancel button or the cross button in the modal | 2024-03-19 | Modal disapears, no action is taken. | Modal disapears, no action is taken. | PASS
9 | Admin clicks on the update button | 2024-03-19 | Admin should get redirected to the update.php page | Admin gets redirected to the update.php page | PASS
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE
| Player list & profile testing | MEDIUM | 4 | 2 | 2024-04-10
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE
| Testing player list and profile |  | Dominik Subocz | Dominik Subocz | 2024-04-10
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| During this test, small tests will be carried out to see if the player list and player profile work as expected. This includes players, juniors and members. |  | Login.php - user must be logged in.
1 | A member tries to access any of the list pages | 2024-04-10 | User should be redirected to logout page | User should be redirected to logout page | PASS
2 | A member gets redirected to their profile page. | 2024-04-10 | Member should see information about them - they shouldn't be able to see or click remove or update buttons | Member see information about them - they don't see any buttons | PASS
3 | Coach/Admin tick the box to select one of the users | 2024-04-10 | Action buttons pop up for that row | Action buttons pop up for that row | PASS
4 | Coach/Admin click update skill button | 2024-04-10 | They should be redirected to update skills page for the selected player/junior | They get redirected to update skills page for the selected player/junior | PASS
5 | Admin clicks on update button | 2024-04-10 | Admin should be redirected to update page for the selected player/junior | Admin gets redirected to update page for the selected player/junior | PASS
6 | Admin clicks on remove button | 2024-04-10 | Admin should be redirected to delete page for the selected player/junior | Admin gets redirected to delete page for the selected player/junior | PASS
7 | Admin/Coach click on the settings button | 2024-04-10 | Settings modal appears | Settings modal appears | PASS
8 | Admin/Coach tick off fields they don't want to see | 2024-04-10 | Unselected fields get hidden | Unselected fields get hidden | PASS

## Add Player Testing
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Add player Testing | HIGH | 5 | 1 | 2024-03-19 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing how the add player system works |  | Dominik Subocz | Dominik Subocz | 2024-03-19 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to see how the player addition system acts under different circumstances and if it works as expected |  | Login.php - user must be logged in, must be admin.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Admin wants to add a new player, they fill out the form with new player credentials | 2024-03-19 | Player gets added successfully and appears on the list. | Player was added successfully and appears on the list. | PASS | Redirect to success page or player list instead to show results
2 | Admin wants to add a new player, they fill out the form with existing player credentials | 2024-03-19 | Error message should pop up saying "User already exists" | Error pops up saying "User already exists" | PASS
3 | Admin fills out the form but some required fields are empty | 2024-03-19 | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | PASS
4 | Admin fills out entire form but they add upload image that is not in the "images" directory | 2024-03-19 | Player should get added successfully and appears on the list - the image should be uploaded to "images" directory | Player gets added successfully and appears on the list - the image is uploaded to "images" directory | PASS | Weird, last time I was trying this, the image wasn't getting added, and no image appears - now it works but I didn't chane code. Maybe some images work and some don't
5 | Admin fills out the form with existing address details | 2024-03-19 | Player should get added with the existing address - No new address record should be created | Player gets added with the existing address - No new address record gets be created | PASS
6 | Admin fills out the form with existing doctor details | 2024-03-19 | Player should get added with the existing address - No new doctor record should be created | Player gets added with the existing address - No new doctor record gets be created | PASS
7 | Admin fills out the form with new address details | 2024-03-19 | Player should get added with the new address - New address record should be created | Player gets added with the new address - New address record gets be created | PASS
8 | Admin fills out the form with new doctor details | 2024-03-19 | Player should get added with the new address - New doctor record should be created | Player gets added with the new address - New doctor record gets be created | PASS

## Add Junior Testing
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Add junior Testing | HIGH | 6 | 1 | 2024-03-19 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing how the add junior system works |  | Dominik Subocz | Dominik Subocz | 2024-03-19 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to see how the junior addition system acts under different circumstances and if it works as expected |  | Login.php - user must be logged in, must be admin.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Admin wants to add a new junior, they fill out the form with new junior credentials | 2024-03-19 | junior gets added successfully and appears on the list. | junior was added successfully and appears on the list. | PASS | Redirect to success page or junior list instead to show results
2 | Admin wants to add a new junior, they fill out the form with existing junior credentials | 2024-03-19 | Error message should pop up saying "User already exists" | Error pops up saying "User already exists" | PASS
3 | Admin fills out the form but some required fields are empty | 2024-03-19 | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | PASS
4 | Admin fills out entire form but they add upload image that is not in the "images" directory | 2024-03-19 | junior should get added successfully and appears on the list - the image should be uploaded to "images" directory | junior gets added successfully and appears on the list - the image is uploaded to "images" directory | PASS
5 | Admin fills out the form with existing address details | 2024-03-19 | Junior should get added with the existing address - No new address record should be created | Junior gets added with the existing address - No new address record gets be created | PASS
6 | Admin fills out the form with existing guardian details | 2024-03-19 | Junior should get added with the existing address - No new guardian record should be created | Junior gets added with the existing address - No new guardian record gets be created | PASS
7 | Admin fills out the form and adds 2 guardians | 2024-03-19 | Junior should get added with the two guardians | Junior gets added with the two guardians | PASS
8 | Admin fills out the form with existing doctor details | 2024-03-19 | Junior should get added with the existing address - No new doctor record should be created | Junior gets added with the existing address - No new doctor record gets be created | PASS
9 | Admin fills out the form with new address details | 2024-03-19 | Junior should get added with the new address - New address record should be created | Junior gets added with the new address - New address record gets be created | PASS
11 | Admin fills out the form with new guardian details | 2024-03-19 | Junior should get added with the new guardian - New guardian record should be created | Junior should get added with the new guardian - New guardian record should be created | PASS
11 | Admin fills out the form with new doctor details | 2024-03-19 | Junior should get added with the new address - New doctor record should be created | Junior gets added with the address - New doctor record gets be created | PASS

## Add Member Testing
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Add member Testing | HIGH | 7 | 1 | 2024-03-19 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing how the add member system works |  | Dominik Subocz | Dominik Subocz | 2024-03-19 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to see how the member addition system acts under different circumstances and if it works as expected |  | Login.php - user must be logged in, must be admin, new members can also access this page to fill out their details to complete registration
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Admin wants to add a new member, they fill out the form with new member credentials | 2024-03-19 | member gets added successfully and appears on the list. | member was added successfully and appears on the list. | PASS | Redirect to success page or member list instead to show results
2 | Admin wants to add a new member, they fill out the form with existing member credentials | 2024-03-19 | Error message should pop up saying "User already exists" | Error pops up saying "User already exists" | PASS
3 | Admin fills out the form but some of the required fields are empty | 2024-03-19 | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | PASS
4 | Admin fills out entire form but they add upload image that is not in the "images" directory | 2024-03-19 | member should get added successfully and appears on the list - the image should be uploaded to "images" directory | member gets added successfully and appears on the list - the image is uploaded to "images" directory | PASS
5 | Member fills out their details after being redirected from registration page and submits the form | 2024-03-19 | member should get redirected to success page and should get rediretced after 5 seconds to logout php where they will need to sign in again | member does not get redirected to success page | FAIL | Add automatic redirection
6 | Admin fills out the form with existing address details | 2024-03-19 | Member should get added with the existing address - No new address record should be created | Member gets added with the existing address - No new address record gets be created | PASS
7 | Admin fills out the form with new address details | 2024-03-19 | Player should get added with the new address - New address record should be created | Player gets added with the new address - New address record gets be created | PASS
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE
| Add member Testing | HIGH | 7 | 2 | 2024-04-10
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE
| Testing how the add member system works |  | Dominik Subocz | Dominik Subocz | 2024-04-10
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to see how the member addition system acts under different circumstances and if it works as expected |  | Login.php - user must be logged in, must be admin, new members can also access this page to fill out their details to complete registration
1 | Member fills out their details after being redirected from registration page and submits the form | 2024-04-10 | member should get redirected to success page and should get rediretced after 5 seconds to logout php where they will need to sign in again | member gets redirected to success page and gets rediretced after 5 seconds to logout php where they will need to sign in again | PASS

## Update Player Testing
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Update player Testing | HIGH | 8 | 1 | 2024-03-19 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing how the update player system works |  | Dominik Subocz | Dominik Subocz | 2024-03-19 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to see how the player addition system acts under different circumstances and if it works as expected |  | Login.php - user must be logged in, must be admin.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Admin fills out the update form with new updated credentials. | 2024-03-19 | Player's information should get updated and changes should be reflected on the list | Player's information gets updated and changes are reflected on the list | PASS | Weird, the image upload I mentioned earlier seems to work with some images and not with other images even if they have a valid image file, perhaps it has to do with the size, but it passes validation so dunno
2 | Admin fills out the update form but the credentials are the same | 2024-03-19 | Player's information should get updated, but nothing will actually get changed. | Player's information should get updated, but nothing will actually get changed | PASS
3 | Admin fills out the form but some required fields are empty | 2024-03-19 | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | PASS
4 | Admin fills out the form with existing address details | 2024-03-19 | Player should get updated with the existing address - No new address record should be created | Player gets updated with the existing address - No new address record gets be created | PASS
5 | Admin fills out the form with existing doctor details | 2024-03-19 | Player should get updated with the existing address - No new doctor record should be created | Player gets updated with the existing address - No new doctor record gets be created | PASS
6 | Admin fills out the form with new address details | 2024-03-19 | Player should get updated with the new address - New address record should be created | Player gets updated with the new address - New address record gets be created | PASS
7 | Admin fills out the form with new doctor details | 2024-03-19 | Player should get updated with the new address - New doctor record should be created | Player gets updated with the new address - New doctor record gets be created | PASS

## Update Junior Testing
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Update junior Testing | HIGH | 9 | 1 | 2024-03-19 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing how the update junior system works |  | Dominik Subocz | Dominik Subocz | 2024-03-19 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to see how the junior addition system acts under different circumstances and if it works as expected |  | Login.php - user must be logged in, must be admin.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Admin fills out the update form with new updated credentials. | 2024-03-19 | Junior's information should get updated and changes should be reflected on the list | Junior's information gets updated and changes are reflected on the list | PASS | Weird, the image upload I mentioned earlier seems to work with some images and not with other images even if they have a valid image file, perhaps it has to do with the size, but it passes validation so dunno
2 | Admin fills out the update form but the credentials are the same | 2024-03-19 | Junior's information should get updated, but nothing will actually get changed. | Junior's information should get updated, but nothing will actually get changed | PASS
3 | Admin fills out the form but some required fields are empty | 2024-03-19 | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | PASS
4 | Admin fills out the form with existing address details | 2024-03-19 | Junior should get updated with the existing address - No new address record should be created | Junior gets updated with the existing address - No new address record gets be created | PASS
5 | Admin fills out the form with existing guardian details | 2024-03-19 | Junior should get updated with the existing address - No new guardian record should be created | Junior gets updated with the existing address - No new guardian record gets be created | PASS
6 | Admin fills out the form and adds 2 guardians | 2024-03-19 | Junior should get updated with the two guardians | Junior gets updated with the two guardians | PASS
7 | Admin fills out the form with existing doctor details | 2024-03-19 | Junior should get updated with the existing address - No new doctor record should be created | Junior gets updated with the existing address - No new doctor record gets be created | PASS
8 | Admin fills out the form with new address details | 2024-03-19 | Junior should get updated with the new address - New address record should be created | Junior gets updated with the new address - New address record gets be created | PASS
9 | Admin fills out the form with new guardian details | 2024-03-19 | Junior should get updated with the new guardian - New guardian record should be created | Junior should get updated with the new guardian - New guardian record should be created | PASS
10 | Admin fills out the form with new doctor details | 2024-03-19 | Junior should get updated with the new address - New doctor record should be created | Junior gets updated with the address - New doctor record gets be created | PASS

## Update Member Testing
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Update member Testing | HIGH | 10 | 1 | 2024-03-19 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing how the update member system works |  | Dominik Subocz | Dominik Subocz | 2024-03-19 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to see how the member addition system acts under different circumstances and if it works as expected |  | Login.php - user must be logged in, must be admin.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Admin fills out the update form with new updated credentials. | 2024-03-19 | member's information should get updated and changes should be reflected on the list | member's information gets updated and changes are reflected on the list | PASS | Weird, the image upload I mentioned earlier seems to work with some images and not with other images even if they have a valid image file, perhaps it has to do with the size, but it passes validation so dunno
2 | Admin fills out the update form but the credentials are the same | 2024-03-19 | member's information should get updated, but nothing will actually get changed. | member's information should get updated, but nothing will actually get changed | PASS
3 | Admin fills out the update form but the credentials are the same | 2024-03-19 | Junior's information should get updated, but nothing will actually get changed. | Junior's information should get updated, but nothing will actually get changed | PASS
4 | Admin fills out the form with existing address details | 2024-03-19 | Member should get updated with the existing address - No new address record should be created | Member gets updated with the existing address - No new address record gets be created | PASS
5 | Admin fills out the form with new address details | 2024-03-19 | Player should get updated with the new address - New address record should be created | Player gets updated with the new address - New address record gets be created | PASS

## Add Game Testing
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Add game Testing | MEDIUM | 11 | 1 | 2024-04-10 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing if the web page for adding games works properly as expected |  | Dominik Subocz | Dominik Subocz | 2024-04-10 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to see how the add game system acts under different circumstances and if it works as expected |  | Login.php - user must be logged in, must be admin or coach.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Admin/Coach fill out entire form to add new game | 2024-04-10 | New game gets created and appears in the timetable page | New game gets created and appears in the timetable page | PASS
2 | Admin/Coach fill out the form but some of the required fields are empty | 2024-04-10 | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | PASS
3 | Admin/Coach prompt dates before today's date | 2024-04-10 | Error message "invalid date" displayed | New game gets created and appears in the timetable page | FAIL | Fix this in future update
4 | Available squads should appear in the drop down input | 2024-04-10 | Available squads appear in the drop down input | Available squads appear in the drop down input | PASS
5 | A new game gets created with blank entries for 2 game halves | 2024-04-10 | A new game gets created with blank entries for 2 game halves | A new game gets created with blank entries for 2 game halves | PASS

## Update Game Testing
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Update game Testing | MEDIUM | 12 | 1 | 2024-04-10 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing if the web page for adding games works properly as expected |  | Dominik Subocz | Dominik Subocz | 2024-04-10 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to see how the game addition system acts under different circumstances and if it works as expected |  | Login.php - user must be logged in, must be admin or coach.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Admin/Coach fill out entire form to update game | 2024-04-10 | Game gets updated and changes are reflected on game profile page | Game gets updated and changes are reflected on game profile page | PASS
2 | Admin/Coach fill out the form but some of the required fields are empty | 2024-04-10 | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | PASS
3 | Admin/Coach prompt dates before today's date | 2024-04-10 | Error message "invalid date" displayed | Game gets updated and appears in the timetable page | FAIL | Fix this in future update
4 | Available squads should appear in the drop down input | 2024-04-10 | Available squads appear in the drop down input | Available squads appear in the drop down input | PASS
5 | game gets updated with blank entries for 2 game halves | 2024-04-10 | Game gets updated with blank entries for 2 game halves | Game gets updated with blank entries for 2 game halves | PASS

## Add Session
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Add training session Testing | MEDIUM | 13 | 1 | 2024-04-10 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing if the web page for adding training sessions works properly as expected |  | Dominik Subocz | Dominik Subocz | 2024-04-10 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to see how the add training session system acts under different circumstances and if it works as expected |  | Login.php - user must be logged in, must be admin or coach.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Admin/Coach fill out entire form to add new training session | 2024-04-10 | New training session gets created and appears in the timetable page | New training session gets created and appears in the timetable page | PASS
2 | Admin/Coach fill out the form but some of the required fields are empty | 2024-04-10 | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | PASS
3 | Admin/Coach prompt dates before today's date | 2024-04-10 | Error message "invalid date" displayed | New training session gets created and appears in the timetable page | FAIL | Fix this in future update
4 | Available squads should appear in the drop down input | 2024-04-10 | Available squads appear in the drop down input | Available squads appear in the drop down input | PASS
5 | Available coaches should appear in the drop down input | 2024-04-10 | Available coaches appear in the drop down input | Available coaches appear in the drop down input | PASS
6 | A new training session gets created with blank entry for training details | 2024-04-10 | A new training session gets created with blank entry for training details | A new training session gets created with blank entry for training details | PASS

## Update Training Session Testing
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| Update training session Testing | MEDIUM | 14 | 1 | 2024-04-10 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing if the web page for adding training sessions works properly as expected |  | Dominik Subocz | Dominik Subocz | 2024-04-10 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to see how the training session addition system acts under different circumstances and if it works as expected |  | Login.php - user must be logged in, must be admin or coach.
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | Admin/Coach fill out entire form to update training session | 2024-04-10 | training session gets updated and changes are reflected on training session profile page | training session gets updated and changes are reflected on training session profile page | PASS
2 | Admin/Coach fill out the form but some of the required fields are empty | 2024-04-10 | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | General error message displayed on top of the form. Specific error message displayed above the field with missing input. | PASS
3 | Admin/Coach prompt dates before today's date | 2024-04-10 | Error message "invalid date" displayed | Training session gets updated and appears in the timetable page | FAIL | Fix this in future update
4 | Available squads should appear in the drop down input | 2024-04-10 | Available squads appear in the drop down input | Available squads appear in the drop down input | PASS
5 | Available coaches should appear in the drop down input | 2024-04-10 | Available coaches appear in the drop down input | Available coaches appear in the drop down input | PASS
6 | Training details should update along with training session records and changes should be reflected on training session's profile | 2024-04-10 | Trainining details changes are reflected on the session's profile along with training session info | Trainining details changes are reflected on the session's profile along with training session info | PASS

## All Delete Pages Testing
SIMPLY RUGBY SYSTEM TESTING DOCUMENT
| TEST TITLE | PRIORITY | TEST CASE ID | TEST NUMBER | TEST DATE |  | PRIORITY KEY
| All delete pages testing | MEDIUM | 15 | 1 | 2024-04-10 |  | LOW
| TEST DESCRIPTION |  | TEST DESIGNED BY | TEST EXECUTED BY | EXECUTION DATE |  | MEDIUM
| Testing if the all the delete pages work as expected |  | Dominik Subocz | Dominik Subocz | 2024-04-10 |  | HIGH
| TEST DESCRIPTION |  | TEST DEPENDENCIES | TEST CONDITIONS |  | TEST CONTROL
| Small tests will be carried out to check if the delete pages work as expected, if they delete records, security level checks, and deletion of associated data |  | Login.php - user must be logged in, must be admin
STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
1 | A player/junior/member/coach try to access one of the delete pages | 2024-04-10 | Levels without admin priveledges get redirected to logout page | Levels without admin priveledges get redirected to logout page | PASS
2 | Admin tries to delete something that is used in another table | 2024-04-10 | Error message "Cannot delete something because it is used in another table" displayed | Error message "Cannot delete something because it is used in another table" displayed | PASS
3 | Admin tries to delete something (not used in any other table) | 2024-04-10 | That data gets removed from database and admin is redirected back to the corresponding page | That data gets removed from database and admin is redirected back to the corresponding page | PASS
4 | Associated data like associations, skills, positions, training details and game halves get removed, if admin clicks on the remove button | 2024-04-10 | Associated data gets deleted from database and admin is redirected back to the corresponding page | Associated data gets deleted from database and admin is redirected back to the corresponding page | PASS